Bovey Parish Neighbourhood Plan

Minutes of the 5th Steering Group Meeting

5th April 2018 at 7.00 pm

Attending:

Mark Bailey (MB)

Cllr Jan Blair (JB)

Marion Edwards (ME)

Cllr Martyn Evans (MTE)

Martin Iles (MI)

Cllr Eoghan Kelly (EK) - Chair

Cllr Steven Leigh

Amber McDonald (AMD)

(Lisa Robillard Webb – Minute-taker and Cllr John Goodey, Exminster & Kenn Valley)

- Apologies –Cllr Uli Arnold (UA), Julie Arnold (JA), Moaki Critchlow-Bunce (MCB), Tom Wilson (TW)

- * Declaration of Interests – Hand into Mark Wells.  Town Councillors are also required to complete one.

- 3.1 Review of Minutes of the Previous Meeting (08/03/2018).  The Minutes were unanimously agreed.

3.2 Review of Actions.

- Communities Fair - Completed

- Unknown -  engagement through social media

- Article in Mid Devon Advertiser published.  Funding found for the questionnaire analysis.

- See 5.2

- See 2)*

- Chair/Vice Chair Updates. Chair update covered elsewhere in meeting. No Vice Chair update available.

- 5.1 Questionnaire Task Group Update: (MB) 1197 questionnaires completed (452 paper copies) which is approximately 10% printed.  Notable points: Not many business responses received but larger firms may have done online questionnaire.  Respondents liked Bovey because it is friendly and rural, but they disliked traffic problems, parking, developments, school situation, surgery and dog mess.  23 Paper Respondents indicated that they would like to volunteer.  A Volunteers’ Meeting is to be held at the Distillery at 7pm on 18th April.  All volunteers now and from past communications should be invited. NPSG members encouraged to attend.

5.2 Draft Plan/ Structure: (ME) Draft plan discussed.  Thame MP used as a template.  Use Appendices for details and keep the plan to the minimum needed.  The plan’s ‘Contents’ will be shaped up in response to the questionnaire results and ‘Education’ will be added.  Mark Wells and Teignbridge District Council will be able to supply some of the background information on Bovey Tracey.  Devon Wildlife Trust can provide an Ecological Report for £65 plus VAT, they specialise in reports for Neighbourhood Plans. Suitable photos for the Plan will need to be sourced. Group agreed to this initial plan as a draft.

- 6.1 Communications (Internal): All agreed to ME’s suggestion that NPSG members in their e mails:

  - Change the e mail’s subject title when a new matter is being discussed

  - Reply only to e mails personally sent to them

  - Sender offers a deadline for replies, otherwise the group will assume agreement with the content

  - Read and file ‘cc’ messages.  Only reply if they do not agree or have a vital point to make.  Use common sense.

6.2 Communications (External):

  - Neighbourhood Plan News Issue 3 to go onto Town Council website.  Alert via social media.

  - Stall at Green Man Festival on 28th April.  NPSG members needed to be on the stall.  EK has promotional materials.

  - Summer Horticultural Show on 18th August

  - All agreed to help compile a calendar of local events for 2018 (eg Local AGMs, Contemporary Craft Fair, School Fair, Phoenix Trust etc).  E mail event dates to EK by 18th April. Volunteers could help at these events.  All agreed to the compilation of event dates.

- Treasurer’s Report.  Available in the Agenda e mail.  Mark Wells writing subjects for the Budget Planner.

- Steering Group vacancy. Vacancy still available.

- Overall Timeline - 9.1 Tracked Progress/Forthcoming Tasks:  In the next few weeks the NPSG will be working on the consultation feedback.  Members to work on own individual actions.

- 10.1 TDC Settlement Boundary Review training.

JB & ME attending this training on 10th April. They will report any urgent issues to the group.

10.2 Neighbourhood Planning.

NPSG members reminded to look at the link: https://www.devoncommunities.org.uk/Event/neighbourhood-planning

- AOB. ME mentioned that the Thame group had a NP Continuity Committee which this group could consider in the future.

.

- The next Meeting will be on Thursday 3rd May at 7.00 pm

ACTIONS

- All NPSG members to:

  - Complete and return Declaration of Interest form

  - If possible, attend the Volunteers’ Meeting is to be held at the Distillery at 7pm on 18th April

  - If possible, attend the NPSG stall at the Green Man Festival 28th April

  - Send local relevant events to EK by the 18th April to compile a calendar of events for promotion of the NP

  - Look at the link https://www.devoncommunities.org.uk/Event/neighbourhood-planning

- MB to invite all possible volunteers to the Volunteers’ Meeting is to be held at the Distillery at 7pm on 18th April

- ME to add Education to the Contents of the Draft Plan

- EK to compile a calendar of events for promotion of the NP

- MCB to update NPSG on the website design and content. Also use of social media.